## Slide 1: Dashboard for Management of Data Repositories on IRIS High-performance Database Service
George Beckett, Edinburgh,
IRIS Digital Asset Workshop, 17th December 2019

## Slide 2: Recall IRIS High-performance Database Service
Tailored storage and compute resources for hosting large-scale data collections (typically database)
  2 × 500 TB storage capacity (Ceph clusters)
  400 compute cores
  40 Gbps network, connected to JANET
  Running (IRIS-compliant) Scientific OpenStack
Motivated by survey astronomy
  Next-generation surveys with multi-PB catalogues
  Move from workstation-class computing to scalable cloud
Aim to identify and include non-astronomy cases too

## Slide 3
Volume Storage – OS / … (small)
Test Storage (500TB)
Database Hosting—Traditional
Ceph
Bare-metal
SQL
ODBC/ RDBMS
Portal
Ingest Service
SSH?
Jupyter
OpenStack (small compute)
AAA
IRIS AIM?
Working Storage
OpenStack (big compute)
Compute
Edinburgh
Man/ RAL/ Cam …
Transient/ Persistent Storage ???
Production Storage (500TB)
Inst. login

## Slide 4: IRIS Digital Asset Call 2019/2020
Objectives
  Streamline creation and management of databases in IRIS
    Focus on large, persistent data repositories, curated by science teams
    Reduce effort required to administer IRIS service
  Image repository of key database technologies
  Integrate into IRIS
    Ensure dashboard compatible with Scientific OpenStack
    Enable access to third-party datasets and other IRIS services
    Provide guidance to RSAP on how to measure/allocate database resources
  Develop policy for end-user database creation
    Extend service to support dynamic, ephemeral (working) databases

## Slide 5: Outputs
D1.1: Customised dashboard for O/S Horizon and O/S CLI
  Streamline creation/ management of database platforms for science teams
D1.2: Suite of images
  Addressing most important relational/ “no-SQL” platforms
D1.3: IRIS integration tools/ configurations
  RSAP templates/ guidance
  Integration of third-party data collections
  Data ingestion
  (Look at streamlining setup of UI (TAP server, web service, etc.) if time permits)
D1.4: User Documentation
D2.1: Best Practice Guide for user-generated working databases
D2.2: AUP template

## Slide 6: Progress
D1.1: Customised dashboard for O/S Horizon and O/S CLI
  OpenStack Trove running on test-bed system
  Experimenting with data-storage provision via Cinder
  Test catalogue (UKIDSS DR9) ingested and setup
  Need to get to grips with Kolla (O/S service config.) w/ help of StackHPC
D1.2: Suite of images
  Image for MySQL Version 5.7 – required for test catalogue (UKIDSS DR9)
  Should be straightforward to add other DBs
D1.3: IRIS Integration
  To start
D1.4: User Documentation
  In progress

## Slide 7: Screenshots
Taken from instance on LSST:UK Test-bed

## Slide 8
Trove adds new menu option to Horizon dashboard

## Slide 9
The Instances sub-menu gives details of user’s instances, along with details of their configure, status and data store

## Slide 10
When creating new Instance, one gets a custom setup, which incorporates database-specific elements.

## Slide 11
Set up database’s connectivity

## Slide 12
One can perform basic DB configuration as part of creation process

## Slide 13
Apply template configurations and replicate from existing database

## Slide 14: Risks and issues
Running around 3 weeks behind schedule
  Due to change of staffing in November (original developer left)
  Potential for WP2 to be de-scoped/ overrun
Database performance
  Benchmarking suggests 2× slow-down for Ceph-based databases c.f. bare-metal DB server
  Experiments to reduce slow-down in progress
Availability of IP addresses
  IPv. 4 addresses are limited
  Unclear of path to IPv.6
  Experimenting with work-arounds such as NAT and port-forwarding

## Slide 15: Thank-you