## Slide 1: LSST Jupyterhub Pilot 9 months on
Gareth Francis
g.francis@epcc.ed.ac.uk

## Slide 2: Project Overview
Jupyter notebooks are becoming popular amongst astronomers as a convenient way to explore and analyse data
The Jupyter notebook is part of the LSST Science Platform Design
Objective of this project is to pilot a JupyterHub service that will ultimately be deployed as part of the LSST UK Data Access Centre

## Slide 3: Recap: status in April 2019
JupyterHub service running on STFC Cloud at RAL
Using Rancher to manage to K8s cluster
Mildly customised Jupyter server (preinstalled libraries)
Integrated with
  EGI Check-in for AAI
  ELK stack for logging
  Git preinstalled & UI plugin for JupyterLab

## Slide 4: Architecture as of April 2019
OpenStack
Kubernetes
Rancher
Docker repo
Proxy
ELK
JHub
GitHub
Check-in
Jupyter
Jupyter
Jupyter

## Slide 5: What we’ve done since
Got some users
  18 unique users
  Monthly usage peaked at 256 hours by 5 users in August
Implemented usage accounting
  Includes support for groups
  Based on XDMoD
  Uses a simple REST service that JupyterHub event hooks can call to write log events
  Also keeps track of real name to username mapping

## Slide 7: What we haven’t done (yet)
We have somewhat deprioritised work on JupyterHub in order to focus on other parts of the LSST data broker service so we haven’t yet done much about:
  Database integration
  Service monitoring, backups and general robustness and maturity
  Documentation
Other features on the back burner due to unclear requirements:
  Integration with Spark/external job systems
  Data sharing (other than git)
  Scaling

## Slide 8: Issues so far
EGI Check-in
  Not particularly user-friendly for either end-users or service admins
Cloud reliability
  Intermittent issues with network packet loss, loss of DNS service and Cinder volumes becoming stuck (believed to all be due to the same network fault). First observed in May, finally resolved in October.
  Major issue with loss of access to Cinder volumes at start of December. Ultimately able to avoid any loss of user data, but nearly two months of down time for some users. Required a lot of manual work to resolve.
Rancher
  Good when it works, difficult to recover from errors

## Slide 9: Issues for IRIS
Reliability
Magnum availability
How easily could we move to/replicate at another IRIS cloud?
How easily could another project replicate what we’ve done?